## Product Backlog
Safe-Stay AI — Product Backlog
SWE6011 Agile Programming · Assignment 2 · Numair Alsaleh (2529226)
ID | Epic | User Story | Priority | Sprint | Status | Story Points | Acceptance Criteria (summary) | Subtasks | Notes
SSAI-5 | Authentication & User Management | As a host, I want to register an account so that I can manage my properties | High | Sprint 1 | To Do | 3 | Can register with email/password; duplicate email rejected; host role assigned | Design form UI; DB migration; controller; PHPUnit test; validation
SSAI-6 | Authentication & User Management | As a host, I want to log in so that I can access my dashboard | High | Sprint 1 | To Do | 2 | Login with email/password; wrong credentials rejected; session persists | Login form UI; auth controller; session management; PHPUnit test
SSAI-7 | Authentication & User Management | As a guest, I want to access the portal so that I can get help about my stay | High | Sprint 1 | To Do | 2 | Access via property link; no registration needed; invalid link denied | Guest route; portal view; link validation; PHPUnit test
SSAI-8 | Authentication & User Management | As an admin, I want to manage user roles so that access is controlled | Medium | Sprint 1 | To Do | 2 | Admin can view/change roles; deactivate users; changes instant | Admin view; role update controller; middleware; PHPUnit test
SSAI-9 | Property & Manual Management | As a host, I want to create a property so that guests can be linked to it | High | Sprint 1 | To Do | 3 | Enter name/address; saved to DB; appears on dashboard; validation | Creation form UI; DB migration; controller; PHPUnit test
SSAI-10 | Property & Manual Management | As a host, I want to upload a house manual so that the AI can use it to answer questions | High | Sprint 1 | To Do | 3 | Upload text manual; linked to property; replaceable; success message | Upload UI; DB migration; file controller; link to property; PHPUnit test
SSAI-11 | Property & Manual Management | As a host, I want to edit my property details so that information stays accurate | Medium | Sprint 1 | To Do | 2 | Edit name/address/desc; saved immediately; only owner can edit | Edit form UI; update controller; validation; PHPUnit test
SSAI-12 | Property & Manual Management | As a host, I want to view all my properties so that I can manage them from one place | Medium | Sprint 1 | To Do | 2 | List all properties on dashboard; click to view details; empty state shown | Properties list view; get all controller; empty state UI; PHPUnit test
SSAI-13 | AI Digital Concierge | As a guest, I want to ask a question about the property so that I get an instant answer | High | Sprint 2 | To Do | 3 | Type question; loading indicator shown; Q&A appears in chat window | Chat UI; question controller; loading indicator; PHPUnit test
SSAI-14 | AI Digital Concierge | As a guest, I want to receive a property-specific response so that the answer is relevant | High | Sprint 2 | To Do | 5 | Response from manual only; fallback if not found; multiple questions allowed | OpenAI/Groq integration; prompt engineering; fallback logic; PHPUnit test
SSAI-15 | AI Digital Concierge | As a host, I want the AI to answer from my manual only so that guests receive accurate information | High | Sprint 2 | To Do | 3 | No general knowledge used; no hallucinations; fallback if no manual | Manual parser; constrain prompt; hallucination mitigation; PHPUnit test
SSAI-16 | AI Digital Concierge | As a host, I want to view the Q&A log so that I can see what guests are asking | Medium | Sprint 2 | To Do | 2 | Log shows all Q&A; filtered by property; newest first | DB migration; log list view; get log controller; PHPUnit test
SSAI-17 | Maintenance & Reporting | As a guest, I want to report a maintenance issue so that the host is notified | High | Sprint 2 | To Do | 3 | Describe issue; submit with one click; confirmed; linked to property | Report form UI; DB migration; submission controller; PHPUnit test
SSAI-18 | Maintenance & Reporting | As a host, I want to view open maintenance reports so that I can act on them | High | Sprint 2 | To Do | 2 | List open reports; filter by property; newest first; click for details | Reports list view; get open reports controller; filter; PHPUnit test
SSAI-19 | Maintenance & Reporting | As a host, I want to mark an issue as resolved so that the guest knows it is fixed | Medium | Sprint 2 | To Do | 2 | Resolve button; status updates instantly; logged with timestamp | Resolve button UI; update status controller; timestamp log; PHPUnit test
SSAI-20 | Maintenance & Reporting | As a host, I want to see issue history so that I can track past problems | Low | Sprint 2 | To Do | 2 | View resolved issues; filter by property; reopen option available | History view; get resolved controller; reopen function; PHPUnit test

## Sprint Plan
Safe-Stay AI — Sprint Plan
Sprint | Dates | Goal | Stories | Focus | Status
Sprint 1 | 1 Apr – 14 Apr 2026 | Set up system foundation, implement authentication for all user roles, and enable hosts to create properties and upload house manuals | SSAI-5, SSAI-6, SSAI-7, SSAI-8, SSAI-9, SSAI-10, SSAI-11, SSAI-12 | Auth, Property & Manual Management | In Progress
Sprint 2 | 15 Apr – 25 Apr 2026 | Deliver AI Digital Concierge, guest Q&A, maintenance reporting, complete all testing evidence and submit | SSAI-13, SSAI-14, SSAI-15, SSAI-16, SSAI-17, SSAI-18, SSAI-19, SSAI-20 | AI Concierge, Maintenance, Testing, Report | To Do

## Epic Summary
Safe-Stay AI — Epic Summary
Epic ID | Epic Name | Sprint | Stories | Total Points
SSAI-1 | Authentication & User Management | Sprint 1 | SSAI-5, SSAI-6, SSAI-7, SSAI-8 | 9
SSAI-2 | Property & Manual Management | Sprint 1 | SSAI-9, SSAI-10, SSAI-11, SSAI-12 | 10
SSAI-3 | AI Digital Concierge | Sprint 2 | SSAI-13, SSAI-14, SSAI-15, SSAI-16 | 13
SSAI-4 | Maintenance & Reporting | Sprint 2 | SSAI-17, SSAI-18, SSAI-19, SSAI-20 | 9
Total Story Points