## Product Backlog
Safe-Stay AI - Product Backlog
SWE6011 Agile Programming · Assignment 2 · Numair Alsaleh (2529226)
ID | Type | Epic | Summary | Priority | Sprint | Status | Story Points | Due Date | Acceptance Criteria (Stories)/ Notes (Tasks)
SSAI-1 | EPIC | — | Authentication & User Management - Covers all registration, login, role management and guest portal access | — | Sprint 1 | In Progress | 19 | 1 Apr – 14 Apr
SSAI-5 | STORY | Authentication & User Management | As a host, I want to register an account so that I can manage my properties | High | Sprint 1 | Done | 3 | 6 Apr | Can register with name/email/password; duplicate email rejected; host role auto-assigned; redirects to dashboard
SSAI-6 | STORY | Authentication & User Management | As a host, I want to log in so that I can access my dashboard | High | Sprint 1 | Done | 2 | 7 Apr | Login with email/password; wrong credentials rejected; session persists; password hidden; error messages shown
SSAI-7 | STORY | Authentication & User Management | As a guest, I want to access the portal so that I can get help about my stay | High | Sprint 1 | To Do | 2 | 8 Apr | Access via property link; no login required; correct property shown; invalid link denied
SSAI-8 | STORY | Authentication & User Management | As an admin, I want to manage user roles so that access is controlled | Medium | Sprint 1 | To Do | 2 | 9 Apr | View all users; change roles; changes instant; actions logged
T2 | TASK | Authentication & User Management | Set up local development environment (PHP, Composer, Node, MySQL) | High | Sprint 1 | Done | 1 | 1 Apr | Laravel, MySQL, Node running locally; .env configured
T3 | TASK | Authentication & User Management | Set up Laravel 11 scaffold with React and Inertia.js | High | Sprint 1 | To Do | 2 | 2 Apr | Laravel installed; Inertia + React configured; Vite running
T4 | TASK | Authentication & User Management | Configure GitHub Actions CI pipeline | High | Sprint 1 | To Do | 1 | 2 Apr | CI runs PHPUnit on every push to main branch
T5 | TASK | Authentication & User Management | Create database migrations for all core models | High | Sprint 1 | To Do | 2 | 3 Apr | Migrations for users, properties, manuals, maintenance_issues
T6 | TASK | Authentication & User Management | Install and configure Zephyr in Jira for test management | Medium | Sprint 1 | To Do | 1 | 12 Apr | Zephyr add-on installed; test project configured
SSAI-2 | EPIC | — | Property & Manual Management - Covers property creation, editing, viewing, and house manual upload | — | Sprint 1 | In Progress | 19 | 1 Apr – 14 Apr
SSAI-9 | STORY | Property & Manual Management | As a host, I want to create a property so that guests can be linked to it | High | Sprint 1 | To Do | 3 | 10 Apr | Enter name/address; saved to DB; appears on dashboard; multiple properties allowed; validation on empty fields
SSAI-10 | STORY | Property & Manual Management | As a host, I want to upload a house manual so that the AI can use it to answer questions | High | Sprint 1 | To Do | 3 | 11 Apr | Upload text manual; linked to property; replaceable; AI uses it; success message shown
SSAI-11 | STORY | Property & Manual Management | As a host, I want to edit my property details so that information stays accurate | Medium | Sprint 1 | To Do | 2 | 12 Apr | Edit name/address/desc; saved immediately; only owner can edit; validation on empty fields
SSAI-12 | STORY | Property & Manual Management | As a host, I want to view all my properties so that I can manage them from one place | Medium | Sprint 1 | To Do | 2 | 13 Apr | List all properties on dashboard; click to view details; ordered by date; empty state shown
T1 | TASK | Property & Manual Management | Create application workflow diagrams (host and guest journeys) | High | Sprint 1 | Done | 1 | 1 Apr | HTML/SVG diagrams created; saved to artefacts/workflow-diagrams/
T7 | TASK | Property & Manual Management | Create ER diagram for database design | High | Sprint 1 | To Do | 2 | 3 Apr | ER diagram showing all tables and relationships; saved to artefacts/er-diagram/
T8 | TASK | Property & Manual Management | Design UI mockups for host dashboard and guest portal | High | Sprint 1 | To Do | 2 | 4 Apr | Wireframes for key screens; saved to artefacts/ui-mockups/
SSAI-3 | EPIC | — | AI Digital Concierge - Covers AI Q&A, prompt engineering, hallucination mitigation, Q&A log | — | Sprint 2 | To Do | 22 | 15 Apr – 28 Apr
SSAI-13 | STORY | AI Digital Concierge | As a guest, I want to ask a question about the property so that I get an instant answer | High | Sprint 2 | To Do | 3 | 18 Apr | Type question; loading indicator shown; Q&A appears in chat; empty input rejected
SSAI-14 | STORY | AI Digital Concierge | As a guest, I want to receive a property-specific response so that the answer is relevant to my stay | High | Sprint 2 | To Do | 5 | 19 Apr | Response from manual only; fallback if not found; multiple questions allowed; response within reasonable time
SSAI-15 | STORY | AI Digital Concierge | As a host, I want the AI to answer from my manual only so that guests receive accurate information | High | Sprint 2 | To Do | 3 | 20 Apr | No general knowledge used; no hallucinations; fallback if no manual uploaded; host can test from dashboard
SSAI-16 | STORY | AI Digital Concierge | As a host, I want to view the Q&A log so that I can see what guests are asking | Medium | Sprint 2 | To Do | 2 | 21 Apr | Log shows all Q&A; filtered by property; newest first; host can review anytime
T9 | TASK | AI Digital Concierge | Configure OpenAI or Groq API credentials and environment | High | Sprint 2 | To Do | 1 | 15 Apr | API key in .env; service class scaffolded; connection tested
T10 | TASK | AI Digital Concierge | Export Jira project report as PDF for zip folder | Low | Sprint 2 | To Do | 1 | 23 Apr | Export from Jira; saved to artefacts/ folder
SSAI-4 | EPIC | — | Maintenance & Reporting - Covers maintenance issue reporting, host resolution, history, and risk log updates | — | Sprint 1–2 | To Do | 18 | 1 Apr – 28 Apr
SSAI-17 | STORY | Maintenance & Reporting | As a guest, I want to report a maintenance issue so that the host is notified | High | Sprint 2 | To Do | 3 | 20 Apr | Describe issue; submit with one click; confirmed; linked to property; empty report rejected
SSAI-18 | STORY | Maintenance & Reporting | As a host, I want to view open maintenance reports so that I can act on them | High | Sprint 2 | To Do | 2 | 21 Apr | List open reports; filter by property; newest first; click for details
SSAI-19 | STORY | Maintenance & Reporting | As a host, I want to mark an issue as resolved so that the guest knows it is fixed | Medium | Sprint 2 | To Do | 2 | 22 Apr | Resolve button on report; status updates instantly; logged with timestamp; guest sees updated status
SSAI-20 | STORY | Maintenance & Reporting | As a host, I want to see issue history so that I can track past problems | Low | Sprint 2 | To Do | 2 | 23 Apr | View resolved issues; filter by property; reopen option; ordered by most recently resolved
T11 | TASK | Maintenance & Reporting | Update risk log after Sprint 1 completion | High | Sprint 1 | To Do | 1 | 14 Apr | Review all 5 risks; update probability/impact; document changes
T12 | TASK | Maintenance & Reporting | Prepare final zip folder with all artefacts and README | High | Sprint 2 | To Do | 1 | 24 Apr | Zip contains code, README, all artefact folders
T13 | TASK | Maintenance & Reporting | Update risk log after Sprint 2 completion | High | Sprint 2 | To Do | 1 | 25 Apr | Final review of all 5 risks; document final status

## Sprint Plan
Safe-Stay AI — Sprint Plan
Sprint | Dates | Goal | Stories / Tasks | Focus | Status
Sprint 1 | 1 Apr – 14 Apr 2026 | Set up system foundation, implement authentication for all user roles, and enable hosts to create properties and upload house manuals | SSAI-5,6,7,8 (Auth) · SSAI-9,10,11,12 (Property) · T1-T8, T11 (Tasks) | Auth, Property & Manual Management, Infrastructure | In Progress
Sprint 2 | 15 Apr – 25 Apr 2026 | Deliver AI Digital Concierge, guest Q&A, maintenance reporting, complete all testing evidence and submit | SSAI-13,14,15,16 (AI) · SSAI-17,18,19,20 (Maintenance) · T9,T10,T12,T13 (Tasks) | AI Concierge, Maintenance, Zephyr Testing, Report, Submission | Planned

## Epic Summary
Safe-Stay AI — Epic Summary
Epic ID | Epic Name | Sprint | Stories | Tasks | Story Points
SSAI-1 | Authentication & User Management | Sprint 1 | SSAI-5, SSAI-6, SSAI-7, SSAI-8 | T2 (Env), T3 (Scaffold), T4 (CI), T5 (Migrations), T6 (Zephyr) | 16
SSAI-2 | Property & Manual Management | Sprint 1 | SSAI-9, SSAI-10, SSAI-11, SSAI-12 | T1 (Workflow), T7 (ER Diagram), T8 (UI Mockups) | 15
SSAI-3 | AI Digital Concierge | Sprint 2 | SSAI-13, SSAI-14, SSAI-15, SSAI-16 | T9 (API Config), T10 (Jira Export) | 15
SSAI-4 | Maintenance & Reporting | Sprint 1–2 | SSAI-17, SSAI-18, SSAI-19, SSAI-20 | T11 (Risk S1), T12 (Risk S2), T13 (Zip Folder) | 12
|  |  |  | Total Story Points | 58

## Risk Log
Safe-Stay AI — RMMM Risk Log
# | Risk Description | Type | Probability | Impact | Priority | Mitigation Strategy | Status
R1 | AI hallucinations — model returns inaccurate property-specific answers | Technical | Low | High | Critical | Prompt engineering to constrain responses to manual content only; fallback message if answer not found; tested every sprint | Open
R2 | Time constraint — 25-day delivery window with no prior code written | Schedule | Low | High | Critical | Strict MVP scope; 2-sprint plan; daily progress tracking; no scope creep permitted | Open
R3 | OpenAI API cost or rate limits during development | Technical | Very Low | Medium | Medium | Use Groq free tier during development; mock API responses in PHPUnit tests; switch to real API for demo only | Open
R4 | Laravel/React/Inertia integration issues causing delays | Technical | Very Low | Medium | Medium | TDD catches integration errors early; GitHub Actions CI runs full test suite on every commit | Open
R5 | Loss of artefact evidence (screenshots, Jira data) | Project | Very Low | High | High | All screenshots committed to GitHub artefacts folder immediately after capture; never rely on Jira alone | Open
Sprint 1 Risk Review (14 April 2026) — [Complete at end of Sprint 1]
Sprint 2 Risk Review (25 April 2026) — [Complete at end of Sprint 2]